## Schedule
Task | Required Resources | Deadline | Status | Responsible Person
week 1
Project Setup & Planning |  |  | Completed | Tharindu
Team formation and supervisor setup | Members contact list | 2025-08-06 | Completed | Tharindu
Project proposal development | communication platforms | 2025-08-20 | Completed | Tharindu,Damean,Dinith,Hiruni,Methuli
Functional , nonfunctional requirements | Supervisor list | 2025-08-10 | Completed | Tharindu
Tools and technical requirements |  | 2025-08-13 | Completed | Hiruni
Develop the project schedule | MS Excel / Gantt chart tool | 2025-08-16 | Completed | Damean
week 2
System design | Draw.io |  | Completed | Hiruni
System architecture diagram | Draw.io | 2025-08-25 | Completed | Methuli
Design database schema (MongoDB) | MongoDB, Mongosh | 2025-08-26 | Doing | Methuli,Hiruni
Design database schema (MongoDB) | MongoDB, Mongosh | 2025-08-26 | Doing | Methuli,Hiruni
Design website interface (wireframes/UI) | React, Node.js | 2025-08-26 | Completed | Hiruni
week 3
ML/DL pipeline Development | Python, Pytorch, VS code |  | Completed | Tharindu
Dataset preparation & preprocessing | Kaggle, VS Code, Python | 2025-08-30 | Completed | Tharindu/Dinith
Train ML model LightGBM | Python, Pytorch, VS code | 2025-08-31 | Completed | Tharindu
Train DL model | Python, Pytorch, VS code | 2025-09-01 | Completed | Tharindu
Ensemble integration | Python, Pytorch, VS code | 2025-09-02 | Completed | dinith
week 4,5,6
Backend Development – Sanitization Engine | Python, Pytorch, VS code |  | Completed | Damean
Implement sanitization logic | Python, Pytorch, VS code | 2025-09-11 | Completed | Damean
Validate sanitized files | Python, Pytorch, VS code | 2025-09-12 | Doing | Damean
Backend Development – Integrity Verification | Python, Pytorch, VS code |  | Completed | Dinith
Generate SHA-256 before cleaning | Hashing Algorithms | 2025-09-15 | Completed | Dinith
Generate SHA-256 after cleaning | Hashing Algorithms | 2025-09-17 | Completed | Dinith
week 7,8
Backend Development – Threat Reporting | Python, Pytorch, VS code |  | Completed | Methuli
Create structured JSON report | Python | 2025-09-19 | Completed | Damean
Convert report to PDF/HTML | Python | 2025-09-19 | To be started | Damean
Timestamp & analysis logging | VS Code | 2025-09-21 | Doing | Methuli
Frontend Development | React.js, Node.js, VS Code |  | Completed | Hiruni
Scan Status – Progress bar & real-time updates | React.js, VS Code | 2025-09-05 | Completed | Hiruni
Results Display | React.js | 2025-09-08 | Doing | Hiruni
Mobile Responsiveness | React.js | 2025-09-09 | To be started | Hiruni
week 9
System Integration (REST API / FastAPI) | Python, VS Code |  | Doing | Methuli
Connect frontend upload to backend | Python, VS Code |  | Doing | Tharindu
Workflow Test | VS Code | 2025-09-27 | To be started | Methuli
Secure Storage – Temp storage & auto-deletion | MongoDB, Mongosh | 2025-09-28 | Doing | Hiruni
week 10,11
Unit Testing – Backend modules |  | 2025-09-29 | To be started | Methuli,Hiruni
Integration Testing – End-to-end |  | 2025-09-30 | To be started | Methuli,Hiruni
Security Testing |  | 2025-10-05 | To be started | Dinith
Documentation & Final Delivery | MS Word |  | Doing | Dinith
User Guide – Step-by-step instructions | MS Word | 2025-10-05 | Doing | Dinith
Developer Guide | MS Word | 2025-10-06 | Doing | Dinith/ Damean
finalizing project documents | MS Word | 2025-10-15 | Doing | Tharindu,Damean,Dinith,Hiruni,Methuli